CS 192 Software Engineering II
Implementation Plan
Plink PlastiCS
Date	Activity	Accountability / (Name of Individual)	Comments/Remarks
Jan 28 / Jan 30	Estimate and plan the implementation / Make and sign team contract	Jeynald Endaya	Documents: Plan, Contract, Prioritized RTM
	Formulate Code Review Checklist / Formulate User Acceptance Criteria	Romeo Albano	Documents: Code Review Checklist, User Acceptance Criteria
Feb 04 / Feb 06	Sprint 1 Code, Unit Test / Implement Default linked list module / Implement clear screen	Yzabel Quiñones	[Place here link in github]
	Integration Test features identified in Sprint 1 / System Test Sprint 1 Fix Bug	Jeynald Endaya
Feb 11 / Feb 13	Retest Sprint Release Commit	Romeo Albano	https://github.com/jjlendaya/CS191pinkPlastiCS
	Studying Android animation and drawing / Fix Sprint 1 code issues and architecture / Formulate User Acceptance Criteria	Jeynald Endaya
Feb 18 / Feb 20	Sprint 2 Code & Unit Test / Finish backend for linked list / Finish frontend for all animations	Yzabel Quiñones
	Implement search node and animations / Implement add node and animations	Yzabel Quiñones	Search node not yet done / Add node haven't implemented
Feb 21	Integration Test features identified in Sprint 2 / System Test Sprint 2 Fix Bug	Jeynald Endaya
Feb 23	Finish search node implementation / Implement add node / Improve animation from sprint 2 / Retest	Jeynald Endaya
Feb 25 / Feb 27	EDSA Revolution
	Sprint Release Commit / Fix Sprint 2 code issues and architecture / Formulate User Acceptance Criteria	Romeo Albano	https://github.com/jjlendaya/CS191pinkPlastiCS
Mar 04 / Mar 06	Sprint 3 Code & Unit Test / Implement delete node and animations	Yzabel Quiñones	Delete node not yet done
	Implement Pre-order module / Implement In-order module / Implement Post-order module	Yzabel Quiñones
Mar 11 / Mar 13	Integration Test features identified in Sprint 3 / System Test Sprint 3 / Fix Bug	Jeynald Endaya
	Retest Sprint Release Commit / Fix Sprint 3 code issues and architecture / Formulate User Acceptance Criteria	Romeo Albano	https://github.com/jjlendaya/CS191pinkPlastiCS
Mar 18 / Mar 20	Sprint 4 Code & Unit Test / Implement Pre-order Tree Walk Play / Implement In-order Tree Walk Play / Implement Post-order Tree walk Play	Yzabel Quiñones
	Integration Test features identified in Sprint 4 / System Test Sprint 4 / Fix Bug / Checkpoint Presentation	Jeynald Endaya
Mar 25 / Mar 27	Retest Sprint Release Commit / Fix Sprint 4 code issues and architecture	Romeo Albano	https://github.com/jjlendaya/CS191pinkPlastiCS
	Implement view usage tracker / Debugging of view usage tracker	Yzabel Quiñones
Apr 01 / Apr 03	Holy Week (Holy Wednesday)
	Holy Week (Good Friday)
Apr 08 / Apr 10	Formulate User Acceptance Criteria / Sprint 5 Code & Unit Test / Implement In-order stop / Implement Post-order stop	Yzabel Quiñones
	Integration Test features identified in Sprint 5 / System Test Sprint 5 / Fix Bug	Jeynald Endaya
Apr 15 / Apr 17	Retest Sprint Release Commit / Fix Sprint 5 code issues and architecture / Formulate User Acceptance Criteria	Romeo Albano	https://github.com/jjlendaya/CS191pinkPlastiCS
	Sprint 6 Code & Unit Test / Implement Post-order stop / Finalize backend for binary search tree	Yzabel Quiñones
Apr 22 / Apr 24	Implement default binary search tree module / Implement clear screen	Yzabel Quiñones
	Integration Test features identified in Sprint 6 / System Test Sprint 6 / Fix Bug	Jeynald Endaya	https://github.com/jjlendaya/CS191pinkPlastiCS
Apr 29 / May 1	Retest Sprint Release Commit / Fix Sprint 6 code issues and architecture	Romeo Albano
	Labor Day
May 6	Alpha Testing (Test all functionalities)	Romeo Albano
May 8	Submission of Alpha Testing Results	Romeo Albano	https://github.com/jjlendaya/CS191pinkPlastiCS
May 13	Beta Testing	Romeo Albano
May 15	Submission of Beta Testing Results	Romeo Albano	https://github.com/jjlendaya/CS191pinkPlastiCS
May 20	Course Debriefing	Jeynald Endaya

Expected Number of Sprint Commits: 13
Expected Number of Code Reviews: 13
Expected Number of Software Release: 2 (Alpha and Beta)